## LOP
List of Open Points
Project: Smart Trajectory Planning
| Status: | 3 | 100%
| open | 0 | 0%
| in work | 1 | 33.33%
| solved | 2 | 66.67%
| canceled | 0 | 0%
Priority Level:
| high |  | to solve as fast as possible - possible risk of major timeline delay, deviation from technical content goals, budget overrun, …
| middle |  | to solve as fast as possible - possible risk of minor timeline delay, deviation from technical content goals, budget overrun, …
| low |  | open issues without impact on timeline delay, deviation from technical content goals, budget overrun, …
# | Date of identification | Originator | Category | Sub-Category | Description | Action / Improvement Suggestion | Priority | Status | Responsible | Due Date | proof of effectiveness | LL relevant
1 | 2020-10-21 | Félix Hernández del Olmo | Technical |  | Crear un repositorio de Github donde compartir todos los archivos del proyecto. |  | high | solved | Borja Pintos | 08.11.2020 | https://github.com/bpintos/smart-trajectory-planning
2 | 2020-10-21 | Borja Pintos | Technical |  | Crear un modelo del vehículo para utilizar junto con el algoritmo de aprendizaje por refuerzo. El modelo del vehículo se corresponde a un coche de radio control. | El modelo del vehículo tiene lincado bloques de biblioteca que están almacenados en https://github.com/bpintos/smart-trajectory-planning/tree/main/02_Development/02_Libraries | high | solved | Borja Pintos | 08.11.2020 | https://github.com/bpintos/smart-trajectory-planning/tree/main/02_Development/03_VehicleModel
3 | 2020-10-21 | Félix Hernández del Olmo | Technical |  | Realizar un estudio del libro Reinforcement Learning de Richard S. Sutton y Andrew G. Barto |  | middle | in work | Borja Pintos | 01.02.2021
4
5
Note on C18: the person who identifies a new open point
Note on E18: possible selection depends on category you can add sub-categories on the "category options" tab
Note on F18: Describe open issue
Note on H18: - low - middle - high
Note on I18: - open - in work - solved - canceled
Note on J18: the person who is responsible for the processing
Note on L18: Describe how the effectiveness of the LOP issue was checked (e.g., was checked in document, was implemented in …..
Note on M18: could the open point be relevant for the lessons learnt list, mark it as "yes"

## Category Options
Category
If possible, use the given category options otherwise you can add new sub-categories in the corresponding list on this sheet.
Categories | Sub-Categories financial | Sub-Categories customer
Technical | - | -
Organizational